## Worklog
Date | Member | Work area | Component | Activity | Evidence reference | Observed timestamp range | Observed hours (lower bound) | Estimate basis | Reviewed/confirmed by
2026-09-20 | Krishna Annavaram | Requirement validation | Requirement validation | Add independent requirements-validation suite for CredPilot; Refresh baseline validation report after repository initialisation | 10a2ba4, 2df754f | 2026-09-20 06:08 - 06:09 UTC | 0.02 | Observed span between first and last commit in the session (10a2ba4 to 2df754f). Lower bound: excludes work before the first commit.
2026-09-20 | Krishna Annavaram | Synthetic data, Requirement validation | Synthetic data, Requirement validation | Add the synthetic mortgage data foundation for CredPilot | a726e31 | 2026-09-20 21:36 - 21:36 UTC | not derivable | Single commit - no span is observable between commits, so no lower bound can be derived. Effort is team-attested.
2026-09-21 | Mahesh Rajendra | Education synthetic data | Education synthetic data | feat: add synthetic education loan origination dataset | f28a1fd | 2026-09-21 04:04 - 04:04 UTC | not derivable | Single commit - no span is observable between commits, so no lower bound can be derived. Effort is team-attested.
2026-09-21 | Krishna Annavaram | Mortgage synthetic data, Education synthetic data | Mortgage synthetic data, Education synthetic data, Synthetic data | Unify the synthetic datasets under one product-partitioned root | 362355d | 2026-09-21 05:26 - 05:26 UTC | not derivable | Single commit - no span is observable between commits, so no lower bound can be derived. Effort is team-attested.
2026-09-21 | Krishna Annavaram | Tests, Mortgage/Education policy RAG | Tests, Mortgage/Education policy RAG, Retrieval evaluation, Documentation | Build the multi-product agentic-RAG and vector retrieval subsystem | 09dc15b | 2026-09-21 09:52 - 09:52 UTC | not derivable | Single commit - no span is observable between commits, so no lower bound can be derived. Effort is team-attested.
2026-09-21 | Krishna Annavaram | Tests, Reports / evidence | Tests, Reports / evidence, Evidence regeneration, Context engineering | Complete the agentic-RAG evaluation subsystem and its governance evidence | 7cb2ee7 | 2026-09-21 20:45 - 20:45 UTC | not derivable | Single commit - no span is observable between commits, so no lower bound can be derived. Effort is team-attested.
2026-09-22 | Krishna Annavaram | Tests, Reports / evidence | Tests, Reports / evidence, Governance / documentation, API / UI, Requirement validation, Observability / Phoenix, Other, Guardrails / security, Evaluation | Complete the conversational, MCP-served copilot and its evidence chain; Close the evidence gaps the full validator run exposed; Add the engineering completion report; Close every validator finding that implementation work can close; Integrate LangMem and Guardrails-AI, and reconcile the failure count | 52aa9ba, e6a1ba8, 74ac6fd, b566030, a6a673c | 2026-09-22 04:08 - 07:50 UTC | 3.7 | Observed span between first and last commit in the session (52aa9ba to a6a673c). Lower bound: excludes work before the first commit.
2026-09-22 | Krishna Annavaram | Reports / evidence, Evaluation | Reports / evidence, Evaluation | Add a Gemini-judged grade against the requirements document | 76a8a6b | 2026-09-22 13:44 - 13:44 UTC | not derivable | Single commit - no span is observable between commits, so no lower bound can be derived. Effort is team-attested.

## Commits
Commit | Author | Timestamp (UTC) | Files changed | Components | Subject
10a2ba4 | Krishna Annavaram | 2026-09-20 06:08:46 | 71 | Requirement validation | Add independent requirements-validation suite for CredPilot
2df754f | Krishna Annavaram | 2026-09-20 06:09:55 | 2 | Requirement validation | Refresh baseline validation report after repository initialisation
a726e31 | Krishna Annavaram | 2026-09-20 21:36:32 | 1331 | Synthetic data, Requirement validation | Add the synthetic mortgage data foundation for CredPilot
f28a1fd | Mahesh Rajendra | 2026-09-21 04:04:38 | 260 | Education synthetic data | feat: add synthetic education loan origination dataset
362355d | Krishna Annavaram | 2026-09-21 05:26:29 | 1591 | Mortgage synthetic data, Education synthetic data, Synthetic data | Unify the synthetic datasets under one product-partitioned root
09dc15b | Krishna Annavaram | 2026-09-21 09:52:35 | 113 | Tests, Mortgage/Education policy RAG, Retrieval evaluation, Documentation | Build the multi-product agentic-RAG and vector retrieval subsystem
7cb2ee7 | Krishna Annavaram | 2026-09-21 20:45:43 | 66 | Tests, Reports / evidence, Evidence regeneration, Context engineering | Complete the agentic-RAG evaluation subsystem and its governance evidence
52aa9ba | Krishna Annavaram | 2026-09-22 04:08:47 | 99 | Tests, Reports / evidence, Governance / documentation, API / UI | Complete the conversational, MCP-served copilot and its evidence chain
e6a1ba8 | Krishna Annavaram | 2026-09-22 04:23:38 | 16 | Reports / evidence, Requirement validation, Observability / Phoenix, Other | Close the evidence gaps the full validator run exposed
74ac6fd | Krishna Annavaram | 2026-09-22 04:29:39 | 2 | Other, Governance / documentation | Add the engineering completion report
b566030 | Krishna Annavaram | 2026-09-22 05:54:23 | 27 | Reports / evidence, Tests, Requirement validation, API / UI | Close every validator finding that implementation work can close
a6a673c | Krishna Annavaram | 2026-09-22 07:50:56 | 48 | Requirement validation, Reports / evidence, Guardrails / security, Evaluation | Integrate LangMem and Guardrails-AI, and reconcile the failure count
76a8a6b | Krishna Annavaram | 2026-09-22 13:44:53 | 3 | Reports / evidence, Evaluation | Add a Gemini-judged grade against the requirements document

## Machine evidence
Artifact | Component | Self-recorded generation time | Runtime (s)
eval/results/pipeline_sweep.json | Retrieval evaluation | 2026-09-22T06:41:19+00:00
eval/results/retrieval_ablation.json | Retrieval evaluation | 2026-09-22T06:44:54+00:00
eval/results/retrieval_eval.json | Retrieval evaluation | 2026-09-22T06:47:46+00:00
traces/trace_summary.json | Observability / Phoenix | 2026-09-22T06:48:54+00:00
reports/eval_report.json | DeepEval / agent evaluation | 2026-09-22T06:59:19+00:00 | 621
reports/golden_signals.json | Observability / Phoenix | 2026-09-22T06:59:23+00:00
reports/requirements_judge.json | Requirement validation | 2026-09-22T13:44:01Z
requirements_validation_tests/reports/latest_test_report.json | Requirement validation | 2026-09-22T14:56:19Z | 376.53

## Attestation
Field | Value
Requirement | REQ-008 - Duration ¦ 20 hours
Statement | Krishna Annavaram and Mahesh Rajendra attest that combined project development, testing, evaluation, review and documentation activity for CredPilot met or exceeded the stated 20-hour engagement duration.
Derivation limit | Exact task-level hours are team-attested rather than mechanically derivable from Git history.
Commit window (UTC) | 2026-09-20 06:08 to 2026-09-22 13:44
Elapsed wall-clock (hours) | 55.6
Note on wall-clock | Elapsed wall-clock is the window work happened inside. It is not a measure of effort and is not offered as one.
Session gap convention (hours) | 3
Krishna Annavaram - confirmation
Krishna Annavaram - date
Mahesh Rajendra - confirmation
Mahesh Rajendra - date
Status | PENDING - unsigned until both members complete their own row